## Sheet1
WBS | Activity | Responsible | Est. Duration (hrs) | Earliest Start (ES) | Earliest Finish (EF) | Latest Start (LS) | Latest Finish (LF) | Total Slack
1.1.1 | Team Roles | Team | 0.5 | 0 | 0.5 | 0 | 0.5 | 0
1.2.1 | Write User Stories and Scenarios | Team | 2 | 0.5 | 2.5 | 0.5 | 2.5 | 0
1.2.2 | Have User Stories/Scenarios Approved by Prof. Hobbs | Lauryn (Primary), Team (Secondary) | 0.5 | 2.5 | 3 | 2.5 | 3 | 0
1.2.3 | Prioritize Features for Sprint 1 | Team | 0.5 | 3 | 3.5 | 3 | 3.5 | 0
1.3.1 | Add New Faculty | Luke (Primary), Ashton (Secondary) | 1.55 | 3.5 | 5.05 | 7.95 | 9.5 | 4.45
1.3.2 | Modify Existing Faculty | Lauryn (Primary), Hailey (Secondary) | 5 | 3.5 | 8.5 | 4.5 | 9.5 | 1
1.3.3 | Delete Faculty | Hailey (Primary), Keller (Secondary) | 1 | 3.5 | 4.5 | 8.5 | 9.5 | 5
1.4.1 | Add New Course | Brooks (Primary), Luke (Secondary) | 4 | 3.5 | 7.5 | 5.5 | 9.5 | 2
1.4.2 | Modify Existing Course | Hailey (Primary), Lauryn (Secondary) | 3 | 3.5 | 6.5 | 6.5 | 9.5 | 3
1.4.3 | Delete Course | Lauryn (Primary), Brooks (Secondary) | 5 | 3.5 | 8.5 | 4.5 | 9.5 | 1
1.5.1 | Add New Conflict | Hailey (Primary), Ashton (Secondary) | 4 | 3.5 | 7.5 | 5.5 | 9.5 | 2
1.5.2 | Modify Existing Conflict | Luke (Primary), Lauryn (Secondary) | 4.25 | 3.5 | 7.75 | 5.25 | 9.5 | 1.75
1.5.3 | Delete Conflict | Lauryn (Primary), Luke (Secondary) | 6 | 3.5 | 9.5 | 3.5 | 9.5 | 0
1.6.1 | Add New Lab | Ashton (Primary), Hailey (Secondary) | 5 | 3.5 | 8.5 | 4.5 | 9.5 | 1
1.6.2 | Modify Existing Lab | Brooks (Primary), Lauryn (Secondary) | 4 | 3.5 | 7.5 | 5.5 | 9.5 | 2
1.6.3 | Delete Lab | Luke (Primary), Phin (Secondary) | 2.2 | 3.5 | 5.7 | 7.3 | 9.5 | 3.8
1.7.1 | Add New Room | Keller (Primary), Brooks (Secondary) | 3 | 3.5 | 6.5 | 6.5 | 9.5 | 3
1.7.2 | Modify Existing Room | Keller (Primary), Luke (Secondary) | 4 | 3.5 | 7.5 | 5.5 | 9.5 | 2
1.7.3 | Delete Room | Ashton (Primary), Keller (Secondary) | 5 | 3.5 | 8.5 | 4.5 | 9.5 | 1
1.8.1 | Print Config File / Display the Scheduler | Brooks (Primary), Hailey (Secondary) | 8 | 9.5 | 17.5 | 9.5 | 17.5 | 0
1.9.1 | Run Scheduler | Keller (Primary), Hailey (Secondary), Ashton (Third), Lauryn (Fourth) | 6 | 17.5 | 23.5 | 17.5 | 23.5 | 0